Report of the Head of Planning and Regeneration To Portfolio Holder for Regeneration On 25 February 2021

Local Development Scheme

1.	SUMMARY

- The Local Development Scheme (LDS) is essentially the timetable for the production of the Council’s Gypsy, Traveller and Travelling Showpeople Allocations Development Plan Document (DPD) and Supplementary planning Documents including the Town Centre Masterplan.  It sets out the various stages of the process for the adoption of the documents and indicative dates.

- As part of the Council’s approach this document will need to be adopted by the Council and kept under review.

- A copy of the Draft document is attached as Appendix A.  It will be placed on the Council’s website once adopted and will be updated as and when required.

Key Decision – This is not a key decision as it simply relates to a timetable of forthcoming work.

- RECOMMENDATION

Recommendation to Council

- That the Local Development Scheme, as outlined in Appendix A, be adopted by the Council and have effect from 9 March 2021.

- BACKGROUND

  - The Council adopted the Mansfield District Local Plan in September 2020, the Local Plan makes a commitment to prepare a number of Supplementary Planning Documents (SPDs), Town Centre Masterplan and to continue in the preparation of the Gypsy, Traveller and Travelling Showpeople DPD.

  - The Local Development Scheme (LDS) sets out the timeline for the preparation of the SPDs, Town Centre Masterplan and Gypsy, Traveller and Travelling Showpeople DPD. This is essentially a list of documents the Council will be preparing and when they are expected to be prepared.

  - Appendix A shows the proposed LDS, the timetable indicates that a number of SPDs will be completed by the summer of 2021 including the Planning Obligations and Affordable Housing SPD.

  - It is proposed that work will commence on the Gypsy, Traveller and Travelling Showpeople DPD and that the Council will consult on further site options in autumn 2021. Council resolved on the 22 January 2020 to consult on two further sites at Sheepbridge Lane and Newlands Triangle. Given that the site at Sheepbridge Lane has now been granted planning permission and the length of time that has passed since the initial ‘Options Consultation’ in the summer of 2019 it is considered appropriate to review all of the sites before a further ‘Options Consultation’ is carried out in the autumn. Further reports will be presented to members on the site options before this consultation commences.

  - The Local Plan commits the Council to preparing a Design SPD, the government is now proposing that  local planning authorities prepare local design codes, it is therefore proposed that once further guidance is issued on the preparation of local design codes that this will be included within the LDS and replace the preparation of the Design SPD.

  - The timetable for the review of the Mansfield District Local Plan is not included at this time and the LDS will be updated at a later date to reflect the need to update the plan within five years. As reviews should be completed no later than five years from the adoption date of the plan. The review will need to take account of changing circumstances within the district and updates to national policy.

  - The comments agreed by Overview and Scrutiny will be provided verbally at the meeting.

4	OPTIONS AVAILABLE

4.1	The LDS needs to be updated and therefore the only alternative option is to propose a different set of dates.  However, the current approach is considered to be the best approach at present.

5	RISK ASSESSMENT OF RECOMMENDATIONS AND OPTIONS

| Risk | Risk Assessment | Risk Level | Risk Management |
| --- | --- | --- | --- |
| Reputation | Adopting a new LDS avoids the risk of future criticism that the LDS is not up to date and current | Low. | The new LDS shows that the Council is committed bringing forward a Gypsy and Traveller Site Allocations DPD and Supplementary Planning Documents. |
| Legal | May face legal challenges in the future related to the DPD if we maintain an out of date LDS | Low | The revised LDS would prevent any legal challenge from being successful. |

6.	ALIGNMENT TO COUNCIL PRIORITIES

6.1	Production of a Local Plan is one of the specific actions that need to be undertaken as part of the Corporate Priorities and the Local Development Scheme is central to that.

7.	IMPLICATIONS

7.1 	It is important to note that adoption of this document simply re-enforces our commitment to bringing forward a local plan and it will also help in providing for good community involvement in within the consultation periods.

(a)	Relevant Legislation – The Council is required to prepare a Local Development Scheme under Section 15 of the Planning and Compulsory Purchase Act 2004 (as amended by the Localism Act 2011). It must be made publically available and kept up-to-date to ensure that local communities and interested parties can keep track of progress.

(b)	Human Rights - No impact as the document simply provides a timetable of intended work and is in accordance with legal requirements under the Planning Acts

(c)	Equality and Diversity No impact as the document is a simple work programme in accordance with legal requirements under the Planning Acts

(d)	Climate change and environmental sustainability- No impact as there are no changes to relevant policies as a result of the adoption of this document.

(e)	Crime and Disorder- No impact as there are no changes to relevant policies as a result of the adoption of this document.

(f) 	Budget /Resource- This document does not in itself generate greater costs than those associated with meeting our legal duties.

8.	COMMENTS OF STATUTORY OFFICERS

(a)	Monitoring Officer – No Specific Comments

(b)	Section 151 Officer – No Specific Comments

9.	CONSULTATION

None

10.	BACKGROUND PAPERS

None.

| Report Author | - | Katie Mills |
| --- | --- | --- |
| Designation | - | Planning Policy Team Leader |
| Telephone | - | 01623 463195 |
| E-mail | - | Kmills@mansfield.gov.uk |