MANSFIELD DISTRICT COUNCIL: INTERVENTIONS USED TO ACHIEVE PERFORMANCE TARGETS

| Reference No. |  | MDC SP HSG 1.001 | Description |  | Average re-let time in days (standard voids) |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Lead Officer |  |  | Karen Cretney / Paul Dawson |  | Date Plan Completed: |  |  | March 2022 |  |  |  |  |
| Performance Out-turn |  |  | 2020/2021 |  |  |  |  | 2021/2022 |  |  |  |  |
|  |  |  | Q1 | Q2 | Q3 | Q4 | Full Year | Q1 | Q2 | Q3 | Q4 | Full Year |
| Overall Measure | Target (days) |  | 72.3 | 72.3 | 72.3 | 72.3 | 72.3 (Housemark Covid sector average for MDC) | 39 | 39 | 39 | 39 | 39 (Housemark Covid sector average for MDC) |
|  | Actual |  | 60.03 | 70.48 | 50.5 | 110.34 | 72.83 | 82.43 | 58.38 | 60.76 | 29.57 | 58 |
| Explanation of Current Performance |  |  | We continue to work through the backlog of void properties whereby work was put on hold due to the various restrictions and lockdowns in place, historic voids and new void properties being received. Recent voids data shows that on average 10.08 void properties are received by Housing Repairs whilst returning an average of 12.48 properties per week for re-let. We are experiencing some difficulties with various material supplies due to a number of issues outside of our control, but are working at ways to mitigate this and limit the interruption to our service delivery. |  |  |  |  |  |  |  |  |  |
| Interventions in the last 3 months and evaluation of impact |  |  | Temporary agency staff continue to work alongside the existing voids team to increase the number of trade operatives working within void properties. One of our existing contractors undertaking electrical and upgrade works to our void properties has also been completing the other minor works within the same property to avoid delay between major works and availability of in-house trade staff. |  |  |  |  |  |  |  |  |  |

| MANSFIELD DISTRICT COUNCIL: INTERVENTION PLAN TO ACHIEVE PERFORMANCE TARGETS |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Key Interventions to Achieve Performance | By When | By Who | Resource Implications | Most Significant Risk to Achievement of Intervention | Contingency Intervention for Most Significant Risk | Monitoring Process | Outcomes expected from intervention |
| 1 | Temporary agency staff to be recruited to assist with voids backlog including a charge-hand. | Commenced in September 2021 managed on a rolling programme to support service delivery | Craig Tinsley Jill Finnesey | To be managed by existing voids Team Leader | Poor quality of agency staff recruited | Agreement in place with recruitment agency for quick replacement of underachieving agency staff | Daily and weekly progress to be monitored by voids Team Leader and Karen Cretney | Reduction in backlog of long term void properties |
| 2 | Existing contractor to undertake all void works within properties that they are already undertaking works, for example kitchen installation alongside minor joinery works and decoration. | Already in place and will continue to be monitored as dependent upon level of works required. Major works void contract being looked into with an approximate 6 month timescale to complete tender stage. | Darren Bird John Matthews | To be managed by existing voids Team Leader | Quality of work and time taken to complete works | Regular progress meetings between voids and contractor | Weekly and monthly progress meetings with programme of work in place | Reduction in overall time taken to complete void works where kitchens and bathrooms are required |
| 3 | Bulk order materials | Certain materials already being purchased in greater quantities to increase stock carried in-house. | Karen Cretney John Matthews Colin Ruston | N/A | Lack of products/materials available from current key suppliers and implications of purchasing from other merchants | Liaise with NCC procurement team and internal auditing and compliance to ensure minimal resistance to using other suppliers/merchants whilst still fulfilling all procurement rules | Stock levels to be monitored weekly by Colin Ruston and Karen Cretney. John Matthews and Team Leaders to react to trends in material requirements and liaise with stores to mitigate disruption. | Increased amount of key stock items available in stores to reduce the risk of repairs not being completed due to lack of materials. |
| 4 | A member of Homefinder Staff working with the voids team at Vale Road | Ongoing | Karen Cretney / Paul Dawson | None – same duties being undertaken but from a different base | Staff not wanting to work from Vale Road | The member of Staff needs to be bought in to the idea of the benefits of working within another team | Bi-monthly meetings to ensure that the working arrangement has met the objectives | To ensure better working between Voids Team and Homefinder and Tenancy Services to ensure that void information for advertisements is accurate and voids can be marketed on time with significant cuts to the overall void times. |
| 5 | Lettings adverts being amended to close on different days and shorter bidding periods | Ongoing | Paul Dawson | N/A | No bids being placed for the properties within the timescales of the advert | Ensuring that only carefully selected properties are advertised in this way | Initial 3 month trial to be undertaken until the number of voids is significantly reduced | A quicker overall void period |
| 6 | The use of virtual viewings i.e. viewing by video | Ongoing | Paul Dawson | None - safer working practice for staff and applicants | Not being aware of which voids are ready to let and therefore ready to video | A member of Homefinder working with the voids team to ensure that we know which voids require videos | Initial 6 month trial to be undertaken to see whether this way of viewing works for us and applicants | A saving of 2-3 days on the overall void turnaround of all voids |