MANSFIELD DISTRICT COUNCIL: INTERVENTIONS USED TO ACHIEVE PERFORMANCE TARGETS

| Reference No. |  | SP PR1.002 | Indicator Description |  | The number of Council housing schemes started on site |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Lead Officer |  |  | Rob Purser |  | Date Plan Completed |  |  | 14 April 2022 |  |  |  |  |
| Performance Out-turn |  |  | 2020/2021 |  |  |  |  | 2021/2022 |  |  |  |  |
|  |  |  | Q1 | Q2 | Q3 | Q4 | Full Year | Q1 | Q2 | Q3 | Q4 | Full Year |
| Overall Measure | Target |  |  |  |  |  |  | 0 | 1 | 1 | 1 | 3 |
|  | Actual |  |  |  |  |  |  | 0 | 1 | 0 | 1 | 2 |
| Explanation of Current Performance |  |  | The target for 2021/22 was based on three housing developments starting on site in 2020/21 – Saundby Avenue, Bellamy Road and Centenary Road. Saundby Avenue commenced on site on 12 July 2021 and Bellamy Road started on 14 March 2022. Centenary Road was programmed to start on site in January 2022 however the Architect working on the development left MDC on 12 September 2021 and progress on developing the design slowed down considerably due to a lack of resources to backfill. A recruitment exercise was undertaken however this was unsuccessful. It was agreed that Design Services would procure the services of an external practice to carry out the work that would have otherwise been undertaken in-house. |  |  |  |  |  |  |  |  |  |
| Interventions in the last 3 months and evaluation of impact |  |  | The appointment of an external practice had to be undertaken by way of an open tender because of the estimated cost of the service. The tender opportunity ran from 9 December 2021 to 14 January 2022. The decision to award the contract to the winning practice was taken on 3 February 2022 with the initial meeting taking place at the beginning of March. Design work is now progressing. |  |  |  |  |  |  |  |  |  |

| MANSFIELD DISTRICT COUNCIL: INTERVENTION PLAN TO ACHIEVE PERFORMANCE TARGETS |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Key Interventions to Achieve Performance | By When | By Who | Resource Implications | Most Significant Risk to Achievement of Intervention | Contingency Intervention for Most Significant Risk | Monitoring Process | Outcomes expected from intervention |
| 1 | Appointment of external architects | Complete | Development Manager | Capital cost chargeable to the project | Intervention achieved | No contingency intervention required | Monthly design team meetings | Developed design to allow the Council to tender for a contractor in the summer. |